## Sheet1
📌Ticketing System for Town-Explorer Project
Project Type: Web Application
Tech Stack:
Laravel (Backend)
Vue.js (Fronend)
Inertia.js (client-side routing bridge)
Database: SQLite
Ticket Status
Done |  | Working on it | Error | Later
[TICKET #001] Initialize Laravel & Vue.js Project
Set up Laravel with Jetstream/Inertia.js
Configure Vue.js, Tailwind CSS, and routing
Install necessary dependencies (Laravel Sanctum, Google Maps API)
[TICKET #002] Database & Authentication Setup
Configure MySQL/PostgreSQL database
Set up Laravel Breeze/Jetstream for authentication
Implement user roles (Admin, Tourist, Business Owner)
Core Features Development (Week 3-8)
🗺️ Geolocation & Mapping (High Priority)
[TICKET #003] Integrate Google Maps API
Display interactive map
Show user’s current location
[TICKET #004] Add Tourist Spot Markers on Map
Fetch locations from the database
Display different categories (Food, Resorts, Landmarks)
[TICKET #005] Implement Route & Directions Feature
Generate routes from user location to a selected tourist spot
Optimize for shortest path
🔍 Search & Filtering (Medium Priority)
[TICKET #006] Implement Search Functionality
Allow users to search places by name
Use fuzzy search for better results
[TICKET #007] Filter Places by Category
Add category-based filtering (Restaurants, Resorts, Landmarks)
Implement dropdown or checkbox filters
💬 Reviews & Ratings (Medium Priority)
[TICKET #008] Create Review & Rating System
Users can leave reviews & rate locations
Display average ratings on the place page
[TICKET #009] Implement Like & Bookmark Feature
Allow users to save places for later
Add a favorites section in the user dashboard
Admin Panel Development (Week 9-10)
[TICKET #010] Build Admin Dashboard
Manage locations (CRUD operations)
Approve user-generated reviews
[TICKET #011] Add Business Owner Role
Allow verified business owners to add/update their spots
Restrict access to only their business listings
[TICKET #012] Implement Content Moderation
Flag inappropriate reviews or photos
Admin approval system for new submissions
⛅ Weather API Integration (Low Priority)
[TICKET #013] Display Current Weather Information
Fetch live weather data for the city
Show weather updates on the homepage
🎉 Events & Announcements (Low Priority)
[TICKET #014] Add Event Listings Section
Allow admins to add upcoming festivals & events
Display countdown timers for major events
📱 Offline Mode (PWA Support) (Low Priority)
[TICKET #015] Implement Progressive Web App (PWA)
Cache important data for offline use
Optimize performance for mobile users
Testing & Deployment (Week 13-14)
[TICKET #016] Perform Unit & Feature Testing
Use Laravel PHPUnit for backend testing
Vue Testing Library for frontend components
[TICKET #017] Optimize Performance & SEO
Implement caching for fast loading
Use meta tags for better search ranking
[TICKET #018] Deploy to Production
Set up a VPS (DigitalOcean, Laravel Forge)
Configure SSL, database, and security settings